## Tasks
ID | Name | Stage | DependsOn | MinDays | MaxDays | FixedDays | Resource | Supplier
D1 | Design time cycle | Planning & Design |  | 20 | 35 |  | Design
D2 | Construction evaluation cycle | Planning & Design | D1 | 10 | 20 |  | Eng
D3 | Procurement plan submission | Planning & Design | D2 | 5 | 10 |  | Procurement
H1 | Procurement (materials) | Hull Construction | D3 | 14 | 30 |  | Procurement | SteelCo
H2 | Delivery | Hull Construction | H1 | 3 | 10 |  | Logistics | SteelCo
H3 | Steel preparation (cut, prime) | Hull Construction | H2 | 7 | 14 |  | Yard
H4 | Panel assembly | Hull Construction | H3 | 10 | 18 |  | Yard
H5 | Block assembly | Hull Construction | H4 | 12 | 22 |  | Yard
H6 | Pre-outfitting | Hull Construction | H5 | 10 | 20 |  | Yard
H7 | Erection (block joining) | Hull Construction | H6 | 8 | 16 |  | Yard
H8 | Hull completion | Hull Construction | H7 | 5 | 10 |  | Yard

## Suppliers
Supplier | BaseLeadDays
SteelCo | 14
AltSteel | 12

## Scenarios
Scenario | Param | Value
base | SUPPLIER | SteelCo
supplier_delay | DELAY_DAYS | 14
defects | DEFECT_RATE | 0.15
defects | REWORK_MIN | 2
defects | REWORK_MAX | 6